## Project tracker
Project Task Tracker |  |  |  | Percent over/under to highlighted numbers | 25%
Task | Category | Assigned to | Estimated start | Estimated finish | Estimated work (in hours) | Estimated duration (in days) | Actual start | Actual finish | Actual work (in hours) | Actual duration (in days) | Notes
Menu GUI | Coding | GUI Team | 2024-11-08 | 2024-11-11 | 6 | 3 | 2024-09-01 | 2024-11-05 | 5 | 64
Leaderboard GUI | Coding | GUI Team | 2024-11-08 | 2024-11-11 | 4 | 3 | 2024-09-25 | 2024-10-29 | 6 | 34
Profile GUI | Coding | GUI Team | 2024-11-08 | 2024-11-11 | 5 | 3 | 2024-07-28 | 2024-10-09 | 4 | 71
Settings GUI | Coding | GUI Team | 2024-11-08 | 2024-11-11 | 6 | 3 | 2024-08-07 | 2024-08-26 | 1 | 19
Login GUI | Coding | GUI Team | 2024-11-08 | 2024-11-11 | 4 | 3 | 2024-08-07 | 2024-09-22 | 1 | 45
Library GUI | Coding | GUI Team | 2024-11-08 | 2024-11-11 | 5 | 3 | 2024-09-06 | 2024-09-21 | 6 | 15
Chat GUI | Coding | GUI Team | 2024-11-08 | 2024-11-11 | 10 | 3 | 2024-09-22 | 2024-10-21 | 5 | 29
Chess GUI | Coding | GUI Team | 2024-11-08 | 2024-11-11 | 10 | 3 | 2024-09-21 | 2024-10-31 | 7 | 40
Checkers GUI | Coding | GUI Team | 2024-11-08 | 2024-11-11 | 10 | 3 | 2024-08-07 | 2024-08-17 | 7 | 10
TTT GUI | Coding | GUI Team | 2024-11-08 | 2024-11-11 | 10 | 3 | 2024-08-07 | 2024-08-17 | 7 | 10
Menu GUI Tested | Testing | GUI Team | 2024-11-12 | 2024-11-20 | 8 | 8 | 2024-08-07 | 2024-08-17 | 7 | 10
Leaderboard GUI Tested | Testing | GUI Team | 2024-11-12 | 2024-11-20 | 8 | 8 | 2024-08-07 | 2024-08-17 | 7 | 10
Profile GUI Tested | Testing | GUI Team | 2024-11-12 | 2024-11-20 | 8 | 8 | 2024-08-07 | 2024-08-17 | 7 | 10
Settings GUI Tested | Testing | GUI Team | 2024-11-12 | 2024-11-20 | 8 | 8 | 2024-08-07 | 2024-08-17 | 7 | 10
Login GUI Tested | Testing | GUI Team | 2024-11-12 | 2024-11-20 | 8 | 8 | 2024-08-07 | 2024-08-17 | 7 | 10
Library GUI Tested | Testing | GUI Team | 2024-11-12 | 2024-11-20 | 8 | 8 | 2024-08-07 | 2024-08-17 | 7 | 10
Chat GUI Tested | Testing | GUI Team | 2024-11-12 | 2024-11-20 | 10 | 8 | 2024-08-07 | 2024-08-17 | 7 | 10
Chess GUI Tested | Testing | GUI Team | 2024-11-12 | 2024-11-20 | 10 | 8 | 2024-08-07 | 2024-08-17 | 7 | 10
Checkers GUI Tested | Testing | GUI Team | 2024-11-12 | 2024-11-20 | 10 | 8 | 2024-08-07 | 2024-08-17 | 7 | 10
TTT GUI Tested | Testing | GUI Team | 2024-11-12 | 2024-11-20 | 10 | 8 | 2024-08-07 | 2024-08-17 | 7 | 10
SETUP

## Task Lookup
Task Number | Task Name | Task Description
Task 1
Task 2
Task 3

## Setup
Setup
Category Name | Employee Name
Coding | GUI Team
Testing
Documentation
Design
PROJECTS