## Project tracker
Project Task Tracker |  |  |  | Percent over/under to highlighted numbers | 25%
Task | Category | Assigned to | Estimated start | Estimated finish | Estimated work (in hours) | Estimated duration (in days) | Actual start | Actual finish | Actual work (in hours) | Actual duration (in days) | Notes
Networking Structure Diagram | Design |  | 30-10-2024 | 11-03-2024 | 4 | 3 | 10-31-2024 | 11-02-2024 | 4 | 3
Networking Use Case Description | Design |  | 30-10-2024 | 11-03-2024 | 6 | 3
Networking Use Case Diagram | Design |  | 30-10-2025 | 11-03-2024 | 6 | 3
Networking Classes Constructed | Coding |  | 11-08-2024 | 11-12-2024 | 2 | 4
Networking Stubs Finished | Coding |  | 11-20-2024 | 11-25-2024 | 8 | 8
Networking Testing | Testing |  | 11-25-2024 | 11-27-2024 | 4 | 2
SETUP

## Task Lookup
Task Number | Task Name | Task Description
Task 1
Task 2
Task 3

## Setup
Setup
Category Name | Employee Name
Documentation | Student 1
Coding | Student 2
Testing | Student 3
Design | Student 4
Category 5 | Student 5
Category 6 | Student 6
PROJECTS