## Project tracker
Project Task Tracker |  |  |  | Percent over/under to highlighted numbers | 25%
Task | Category | Assigned to | Estimated start | Estimated finish | Estimated work (in hours) | Estimated duration (in days) | Actual start | Actual finish | Actual work (in hours) | Actual duration (in days) | Notes
Game Functionality | Coding | Game Logic | 2024-11-08 | 2024-11-25 | 40 | 17 | 2024-08-31 | 2024-11-04 | 5 | 64
Game Functionality Testing | Testing | Game Logic | 2024-11-23 | 2024-11-26 | 9 | 3 | 2024-09-24 | 2024-10-28 | 6 | 34
Authentication Functionality | Coding | Authentication | 2024-11-08 | 2024-11-25 | 5 | 17 | 2024-07-27 | 2024-10-08 | 4 | 71
Authentication Functionality Testing | Testing | Authentication | 2024-11-23 | 2024-11-26 | 6 | 3 | 2024-08-06 | 2024-08-25 | 1 | 19
Networking Stubs | Coding | Networking | 2024-11-11 | 2024-11-18 | 4 | 7 | 2024-08-06 | 2024-09-21 | 1 | 45
Player Interaction | Coding | GUI | 2024-11-08 | 2024-11-25 | 35 | 17 | 2024-09-05 | 2024-09-20 | 6 | 15
Player Interaction | Testing | GUI | 2024-11-23 | 2024-11-26 | 8 | 3 | 2024-09-21 | 2024-10-20 | 5 | 29
Integrating separate modules | Coding | Integration | 2024-11-27 | 2024-12-04 | 10 | 7 | 2024-11-03 | 2024-11-05 | 6 | 2
Test integration | Testing | Integration | 2024-11-27 | 2024-12-04 | 1 | 17 | 2024-08-06 | 2024-08-16 | 7 | 10
Leaderboard Functionality | Coding | Leaderboard | 2024-11-08 | 2024-11-25 | 40 | 3 | 2024-08-31 | 2024-11-04 | 5 | 64
Leaderboard Testing | Testing | Leaderboard | 2024-11-23 | 2024-11-26 | 9 | #REF! | 2024-09-24 | 2024-10-28 | 6 | 34
[5 empty] | 5 | #REF! | 2024-07-27 | 2024-10-08 | 4 | 71
[5 empty] | 6 |  | 2024-08-06 | 2024-08-25 | 1 | 19
[5 empty] | 4 |  | 2024-08-06 | 2024-09-21 | 1 | 45
[5 empty] | 35 |  | 2024-09-05 | 2024-09-20 | 6 | 15
[5 empty] | 8 |  | 2024-09-21 | 2024-10-20 | 5 | 29
[5 empty] | 10 |  | 2024-11-03 | 2024-11-05 | 6 | 2
[5 empty] | 1 |  | 2024-08-06 | 2024-08-16 | 7 | 10
SETUP

## Task Lookup
Task Number | Task Name | Task Description
Task 1
Task 2
Task 3

## Setup
Setup
Category Name | Employee Name
Design | Game Logic
Coding | GUI
Documentation | Networking
Testing | Authentication
Category 5 | Leaderboard
Category 6 | Integration
PROJECTS