## Project tracker
Project Task Tracker |  |  |  | Percent over/under to highlighted numbers | 25%
Task | Category | Assigned to | Estimated start | Estimated finish | Estimated work (in hours) | Estimated duration (in days) | Actual start | Actual finish | Actual work (in hours) | Actual duration (in days) | Notes
Leaderboard Classes Constructed | Coding | Leaderboard Team | 2024-11-08 | 2024-11-11 | 20 | 4 |  |  |  | 3
Leaderboard Code Finished | Coding | Leaderboard Team | 2024-11-12 | 2024-11-16 | 32 | 5 |  |  |  | 5
Sample Database Creation | Coding | Leaderboard Team | 2024-11-17 | 2024-11-18 | 16 | 2 |  |  |  | 3
Simulation of Leaderboard Scenarios | Testing | Leaderboard Team | 2024-11-19 | 2024-11-21 | 16 | 3
Leaderboard Code Functional | Testing | Leaderboard Team | 2024-11-22 | 2024-11-24 | 32 | 3
Leaderboard Code Fully Tested | Testing | Leaderboard Team | 2024-11-25 | 2024-11-27 | 16 | 3
Documenting all Requirements | Documentation | Leaderboard Team | 2024-11-25 | 2024-11-27 | 2 | 1
SETUP

## Task Lookup
Task Number | Task Name | Task Description
Task 1
Task 2
Task 3

## Setup
Setup
Category Name | Employee Name
Documentation | Saad Zafar Khan
Coding | Ivan Chen
Testing | Alex Zhou
Prajnya Moola
Guanhua Huang
PROJECTS