## Project tracker
Project Task Tracker |  |  |  | Percent over/under to highlighted numbers | 25%
Task | Category | Assigned to | Estimated start | Estimated finish | Estimated work (in hours) | Estimated duration (in days) | Actual start | Actual finish | Actual work (in hours) | Actual duration (in days) | Notes
Task 1 | Category 1 | Student 1 | 2024-07-12 | 2024-09-10 | 4 | 58 | 2024-07-12 | 2024-09-15 | 5 | 63
Task 2 | Category 2 | Student 2 | 2024-08-05 | 2024-09-05 | 4 | 30 | 2024-08-05 | 2024-09-08 | 6 | 33
Task 3 | Category 1 | Student 3 | 2024-06-07 | 2024-08-06 | 5 | 59 | 2024-06-07 | 2024-08-19 | 4 | 72
Task 4 | Category 2 | Student 4 | 2024-06-17 | 2024-06-27 | 6 | 10 | 2024-06-17 | 2024-07-06 | 1 | 19
Task 5 | Category 3 | Student 5 | 2024-06-17 | 2024-07-27 | 4 | 40 | 2024-06-17 | 2024-08-02 | 1 | 45
Task 6 | Category 4 | Student 6 | 2024-07-17 | 2024-07-27 | 5 | 10 | 2024-07-17 | 2024-08-01 | 6 | 14
Task 7 | Category 5 | Student 2 | 2024-08-02 | 2024-08-26 | 1 | 24 | 2024-08-02 | 2024-08-31 | 5 | 29
Task 8 | Category 2 | Student 2 | 2024-08-07 | 2024-09-15 | 1 | 38 | 2024-08-01 | 2024-09-10 | 7 | 39
Task 9 | Category 4 | Student 2 | 2024-06-12 | 2024-07-02 | 1 | 20 | 2024-06-17 | 2024-06-27 | 7 | 10
SETUP

## Task Lookup
Task Number | Task Name | Task Description
Task 1
Task 2
Task 3

## Setup
Setup
Category Name | Employee Name
Category 1 | Student 1
Category 2 | Student 2
Category 3 | Student 3
Category 4 | Student 4
Category 5 | Student 5
Category 6 | Student 6
PROJECTS