## Project tracker
Project Task Tracker |  |  |  | Percent over/under to highlighted numbers | 25%
Task | Category | Assigned to | Estimated start | Estimated finish | Estimated work (in hours) | Estimated duration (in days) | Actual start | Actual finish | Actual work (in hours) | Actual duration (in days) | Notes
Game Functionality | Coding | Game Logic | 2024-11-08 | 2024-11-25 | 40 | 17 | 2024-08-27 | 2024-10-31 | 5 | 64
Game Functionality Testing | Testing | Game Logic | 2024-11-23 | 2024-11-26 | 9 | 3 | 2024-09-20 | 2024-10-24 | 6 | 34
Authentication Functionality | Coding | Authentication | 2024-11-08 | 2024-11-25 | 5 | 17 | 2024-07-23 | 2024-10-04 | 4 | 71
Authentication Functionality Testing | Testing | Authentication | 2024-11-23 | 2024-11-26 | 6 | 3 | 2024-08-02 | 2024-08-21 | 1 | 19
Networking Stubs | Coding | Student 5 | 2024-11-11 | 2024-11-18 | 4 | 7 | 2024-08-02 | 2024-09-17 | 1 | 45
Task 6 | Category 4 | Student 6 | 2024-09-01 | 2024-09-11 | 5 | 10 | 2024-09-01 | 2024-09-16 | 6 | 15
Task 7 | Category 5 | Student 2 | 2024-09-17 | 2024-10-11 | 1 | 24 | 2024-09-17 | 2024-10-16 | 5 | 29
Task 8 | Category 2 | Student 2 | 2024-09-22 | 2024-10-31 | 1 | 39 | 2024-09-16 | 2024-10-26 | 7 | 40
Task 9 | Category 4 | Student 2 | 2024-07-28 | 2024-08-17 | 1 | 19 | 2024-08-02 | 2024-08-12 | 7 | 10
SETUP

## Task Lookup
Task Number | Task Name | Task Description
Task 1
Task 2
Task 3

## Setup
Setup
Category Name | Employee Name
Design | Game Logic
Coding | GUI
Documentation | Networking
Testing | Authentication
Category 5 | Leaderboard
Category 6 | Integration
PROJECTS