## Project tracker
Project Task Tracker |  |  |  | Percent over/under to highlighted numbers | 25%
Task | Category | Assigned to | Estimated start | Estimated finish | Estimated work (in hours) | Estimated duration (in days) | Actual start | Actual finish | Actual work (in hours) | Actual duration (in days) | Notes
TicTacToe Classes Constructed | Coding | Game Logic Team | 08-11-2024 | 11-11-2024 | 5 | 4 |  |  |  | 1
TicTacToe Code Finished | Coding | Game Logic Team | 12-11-2024 | 19-11-2024 | 8 | 8 |  |  |  | 2
TTT Code Functional | Coding | Game Logic Team | 20-11-2024 | 26-11-2024 | 8 | 7 |  |  |  | 2
TTT Code Fully Tested | Testing | Game Logic Team | 25-11-2024 | 27-11-2024 | 8 | 3
Chess Classes Constructed | Coding | Game Logic Team | 08-11-2024 | 11-11-2024 | 5 | 4
Chess Code Finished | Coding | Game Logic Team | 12-11-2024 | 19-11-2024 | 8 | 8
Chess Code Functional | Coding | Game Logic Team | 20-11-2024 | 26-11-2024 | 8 | 7
Chess Code Fully Tested | Testing | Game Logic Team | 25-11-2024 | 27-11-2024 | 8 | 3
Checkers Classes Constructed | Coding | Game Logic Team | 08-11-2024 | 11-11-2024 | 5 | 4
Chess Code Finished | Coding | Game Logic Team | 12-11-2024 | 19-11-2024 | 8 | 8
Chess Code Functional | Coding | Game Logic Team | 20-11-2024 | 26-11-2024 | 8 | 7
Chess Code Fully Tested | Testing | Game Logic Team | 25-11-2024 | 27-11-2024 | 8 | 3
SETUP

## Task Lookup
Task Number | Task Name | Task Description
Task 1
Task 2
Task 3

## Setup
Setup
Category Name | Employee Name
Documentation | Game Logic Team
Coding
Testing
Category 4
Category 5 | Student 5
Category 6 | Student 6
PROJECTS