## Project tracker
Project Task Tracker |  |  |  | Percent over/under to highlighted numbers | 25%
Task | Category | Assigned to | Estimated start | Estimated finish | Estimated work (in hours) | Estimated duration (in days) | Actual start | Actual finish | Actual work (in hours) | Actual duration (in days) | Notes
Research/Setup | Project It 3 | Integration Team | 2024-11-08 | 2024-11-11 | 2 | 3 | 2024-10-31 | 2024-11-02 | 2 | 2
Research/Setup | Project It 3 | Integration Team | 2024-11-08 | 2024-11-11 | 2 | 3 | 2024-10-31 | 2024-11-02 | 2 | 2
Research/Setup | Project It 3 | Integration Team | 2024-11-08 | 2024-11-11 | 2 | 3 | 2024-10-31 | 2024-11-02 | 2 | 2
Research/Setup | Project It 3 | Integration Team | 2024-11-08 | 2024-11-11 | 2 | 3 | 2024-10-31 | 2024-11-02 | 2 | 2
Integrating | Project It 3 | Integration Team | 2024-11-11 | 2024-11-25 | 10 | 14 | 2024-11-03 | 2024-11-04 | 7 | 1
Integrating | Project It 3 | Integration Team | 2024-11-11 | 2024-11-25 | 10 | 14 | 2024-11-03 | 2024-11-04 | 7 | 1
Integrating | Project It 3 | Integration Team | 2024-11-11 | 2024-11-25 | 10 | 14 | 2024-11-03 | 2024-11-04 | 7 | 1
Integrating | Project It 3 | Integration Team | 2024-11-11 | 2024-11-25 | 10 | 14 | 2024-11-03 | 2024-11-04 | 7 | 1
SETUP

## Task Lookup
Task Number | Task Name | Task Description
Task 1
Task 2
Task 3

## Setup
Setup
Category Name | Employee Name
Project It 3 | Integration Team
Category 2
Category 3
Category 4
Category 5
Category 6
PROJECTS