## Project tracker
Project Task Tracker |  |  |  | Percent over/under to highlighted numbers | 25%
Task | Category | Assigned to | Estimated start | Estimated finish | Estimated work (in hours) | Estimated duration (in days) | Actual start | Actual finish | Actual work (in hours) | Actual duration (in days) | Notes
TTT Structure Diagram | Documentation | Alyvia | 30-10-2024 | 2-11-2024 | 6 | 3 | 31-10-2024 | 01-11-2024 | 2:30 | 1 | 9:00-11:30pm on nov 1st
TTT Use Case Description | Documentation | Alyvia | 30-10-2024 | 2-11-2024 | 6 | 3 | 30-10-2024 | 01-11-2024 | 2:00 | 2 | 7:00-9:00pm on nov 1st
TTT Use Case Diagram | Documentation | Alyvia | 30-10-2025 | 2-11-2024 | 6 | 3 | 30-10-2024 | 01-11-2024 | 3:00 | 2 | 5:00-7:00pm on oct 30th, 6:00-7:00 on nov 1st
Chess SD | Category 2 | Student 4 | 30-10-2026 | 2-11-2024 | 6 | 3
Chess UC Descriptions | Category 3 | Student 5 | 30-10-2027 | 2-11-2024 | 6 | 3
Chess UC Diagrams | Category 4 | Student 6 | 30-10-2028 | 2-11-2024 | 6 | 3
Checkers SD | Category 5 | Student 2 | 30-10-2029 | 2-11-2024 | 6 | 3
Checkers UC Descriptions | Category 2 | Student 2 | 30-10-2030 | 2-11-2024 | 6 | 3
Checkers UC Diagram | Category 4 | Student 2 | 30-10-2031 | 2-11-2024 | 6 | 3
SETUP

## Task Lookup
Task Number | Task Name | Task Description
Task 1
Task 2
Task 3

## Setup
Setup
Category Name | Employee Name
Documentation | Alyvia
Coding | Holden
Testing | Matthew
Category 4 | Ezra
Category 5 | Student 5
Category 6 | Student 6
PROJECTS